## Project Planner
SIT107- Energy efficiency Project
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 4 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Activity and Team Member Assigned | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | Days (3/9/19-27/9/19)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40
Brainstorm an idea for the project (Whole group) | 1 | 2 | 1 | 1 | 100%
Project explanation(Eangheng) | 2 | 3 | 1 | 1 | 100%
Sense-Think-Act Requirements (Mohamed) | 1 | 4 | 1 | 2 | 100%
Data Collection Method (Aaron) | 3 | 7 | 3 | 2 | 100%
Purpose of collecting data( Ryan) | 3 | 7 | 3 | 2 | 100%
Backlog in Trello (Aaron) | 3 | 3 | 4 | 2 | 100%
Burndown Chart (Aaron) | 3 | 4 | 5 | 1 | 100%
User stories (Eangheng and Ryan) | 3 | 3 | 5 | 1 | 100%
Challenges Faced (Aaron) | 3 | 4 | 4 | 2 | 100%
Code writing (Ryan) | 3 | 7 | 3 | 2 | 100%
Demonstration of Prototype (whole group) | 3 | 7 | 3 | 1 | 100%
Future Plans (Aaron) | 3 | 4 | 4 | 2 | 100%
Gantt chart (Mohamed) | 4 | 3 | 4 | 2 | 100%
0%
0%
0%
Total duration | 1 | 22 | 1 | 0 | 0%